### Country:		BELARUS

### COUNTRY PROGRAMME PERFORMANCE SUMMARY

### Reporting period: 	2006-2009

### EXECUTIVE SUMMARY

Socio-economic portfolio

An Investment Policy review was conducted to identify areas for further cooperation that are considered to be deterring investment flows to Belarus. UNDP succeeded in raising the profile of the national debate on poverty related issues; incorporating the National Poverty Reduction Strategy into national socio-economic planning and policies; improving the availability and quality of data for social diagnostics and early warning of high unemployment and poverty risks at the regional level. UNDP strengthened dialogue and partnership between business and the state to have it more constructive and specific. That helped make the policy making processes more transparent, and decreased the state involvement in the economy. By involving business unions in review of business law, UNDP  has produced clear and impressive results in legislative simplification that have helped Belarus secure movement in its world bank ‘ease of doing business’ ranking  from 115 (2007) - to 85 (2009). Capacity of the business support institutions was enhanced to better serve the population in remote/rural areas.  A sound basis for sustained growth of the national microfinance sector was created. Through the global compact initiative UNDP promoted responsible entrepreneurship and engaged businesses in local socio-economic development.

Energy and Environment portfolio

UNDP supported Belarus in building national capacity to combat climate change through development of a long-term strategy for Belarus' participation in the flexible mechanisms of the Kyoto Protocol, along with providing technical support to the country to be able to meaningfully participate in negotiations for the Copenhagen climate conference. UNDP supported the expansion and sustainable operation of the national network of protected natural areas in the biodiversity rich Polessje region. As a result, a trans-boundary Ramsar site is established, the country’s capacity to manage natural protected areas is strengthened, and sustainable livelihood of local communities living inside and in proximity to protected territories is supported. In effective partnership with the Belarusian Ministry of Environment and the Ministry of Forestry, UNDP demonstrated economic and environmental viability of restoration of degraded peatlands, significantly improving the country’s institutional and expert capacity to combat land degradation. Through assisting the Government in building a national system for strategic environmental assessment in Belarus, UNDP promoted integration of environmental concerns into national decision-making. A new secondary school course on biodiversity has been developed in cooperation with a Belarusian NGO, and introduced into the secondary school curricular.

Democratic Governance portfolio

UNDP contributed to broaden understanding and application of the international human rights standards by legal professionals, and to enable the national justice system to become more responsive to the expectations and needs of right holders. Centre for illegal migrants was established in Brest. A 4–volume compendium (of 3200 pages) of the international human rights standards and case–law of the European Court of Human Rights and the UN Human Rights Committee was prepared and published. Its 8,000 hard-copies and 10,000 on CD have been distributed among judges, lawyers, prosecutors, legislators and representatives of executive government authorities, libraries, law universities and NGOs. UNDP also facilitated the development of the legislation which lead to a reform in administrative procedures of the Government of Belarus in line with international practices and contributed to the improvement of practitioners’ capacities in this regard.  In cooperation with other UN agencies, UNDP aimed to enhance effectiveness of the international technical cooperation of Belarus on the basis of harmonization of national regulations with donor regulations. Certain recommendations to improve national regulations of international technical cooperation of Belarus, and to enhance its effectiveness were produced. Drafts legislative acts with supporting background were produced to improve the current system of management of projects of international technical assistance implemented in a NEX modality as well as mini-projects of International Technical Assistance. Further UNDP efforts are focused on rendering assistance to Belarus in joining the Convention on the Rights of Persons with Disabilities and its implementation. Analytical paper on accession to the Convention on the Rights of Persons with Disabilities (PWD) by Belarus, including review of the national legal framework and recommendation for its further improvement, prepared. The analytical paper will be used as a basis for internal government procedures necessary for presenting the draft law on “Accession to the Convention on the Rights of Persons with Disabilities (PWD) by Belarus” to the House of Representatives of the National Assembly. A tool for continuous and comprehensive monitoring of the situation of PWD and of their rehabilitation effectiveness developed and the National Survey of the situation of the PWD launched.

The capacities of the border guards have been strengthened through introduction of automated border control systems at all border check points of Belarus. As a result, the government abolished requirement of the mandatory permit for citizens to travel abroad.  Legal framework pertaining to fighting illicit drugs was improved and the National Drugs Monitoring Centre was set up, law-enforcement agencies were trained on controlled deliveries, clandestine laboratories, modern search techniques and other. Preventing, fighting and addressing the social consequences of trafficking in human beings in Belarus was addressed with the launched awareness-raising campaign, trainings of anti-trafficking institutions/organizations (both governmental and NGOs) in dealing with trafficking in human beings (THB) - proper focus on gender issue was ensured -  preparatory works for a comprehensive research in the field of THB and its further appliance for developing recommendations on preventive measures and victims assistance. Capacity of the Shelter to protect victims and render rehabilitation and reintegration was enhanced and assistance to victims was provided.

Chernobyl portfolio

UNDP assisted the Government in improving the lives of people affected by the Chernobyl disaster by supporting local efforts to improve economic and social conditions including through the CORE Programme and with the introduced ABD approach. UNDP promoted community mobilization in four districts of Brest, Mogilev and Gomel regions. UNDP also facilitated the enhancement of the livelihoods of rural Chernobyl-affected communities and supported provision of medical care services, improved the knowledge of the population, including pregnant women and nursing mothers, ‘reproductive reserve group’ women, future fathers, secondary school teachers and schoolchildren, in radiological issues and monitoring among the most vulnerable groups in these communities. The population was provided with awareness-raising activities and provision of certain medical care services through the established Information and Advisory Centre “Dialogue” as well as 16 Health Fairs organized in the target rural communities. A number of video films on safe foodstuff and proper care for babies as well as books, copy books and coloring books were produced. Youth-oriented projects supported by the Maria Sharapova Foundation led to improved practical ecological skills of children and vocational school students (19 cleaned springs, pet’s corner set up at the District Children’s Arts Centre);  improved cultural and educational level of children and youth through promotion of musical education  in rural areas, arousing rural children’s interest in music, and developing their creative abilities (a number of music school branches in isolated rural areas); established “Fairytale Room” to provide therapy to children in the form of interactive games, mini-circuses and other healing and inspirational activities. UNDP together with the Maria Sharapova Foundation established the first ever in Belarus international scholarship programme in the two major universities in the country to support talented youth from Chernobyl-affected territories. Clear gender dimension is observed in those interventions and the outputs.

Cross-border portfolio

In the area of HIV and tuberculosis, systemic interventions took place. Belarus started treatment of over 1,500 HIV patients with antiretroviral drugs allowing those patients to stay alive and to lead normal lives. The HIV epidemic remained at its stable level thanks to large scale prevention programmes for such vulnerable groups as intravenous drugs users, female sex workers, men having sex with men, and prisoners.  Thanks to tuberculosis grant, national treatment guidelines have been revised, more than 1,500 people are receiving directly observed anti-TB treatment with social support, more than 3,000 national specialists have been trained, 200 patients are receiving treatment from multi-drug resistant tuberculosis.

### II: Country Programme Performance Summary

| Country information |  |
| --- | --- |
| Country name: Belarus |
| Current country programme period: 2006-2010 |
| Outcomes | Total Expenditure (thousands USD) | Key Indicators of outcome (1-4 per outcome) | Progress made against key indicators |
| 1 Better monitoring of the progress towards meeting the MDGs and application of National Human Development Report’s (NHDRs) recommendation in national planning and policy formulation | 1,248 | National indicators for tracking MDGs and poverty-related indicators. Preparation of NHDRs by a national state institution at least bi-annually | a set of non-income poverty-related indicators was proposed 2008-2009 NHDR produced and provided policy recommendations |
| UNDP Contribution: CP Outputs: (a) support the government agencies in designing and collecting disaggregated statistical data and improving poverty monitoring and analysis; (b) NHDR are used for state socio-economic policy formulation and planning. Progress and Achievements: A comprehensive poverty assessment methodology was developed based on international approaches and best practices to capture multi-faceted nature of poverty. Qualitative measures of poverty and a set of non-income indicators (e.g. access to housing and social services, health and education) have been proposed and tested. Several of them have been incorporated by the Ministry of Statistics as separate modules in the National Household Income Survey questionnaire. The 10th NHDR 2008-2009 in Belarus was produced and published by the National Research Institute of Economy under the Ministry of Economy. The report provided recommendations in the area of life expectancy and the influence of national policies on changing the current negative trend of this HDI component for Belarus. |
| 2. Poverty reduction incorporated into national socio-economic planning and policies | 74 | Main principle of the National Poverty Reduction Strategy (NPRS) developed and linked to the State Socio-Economic Development Programme for 2006-2010 and other strategic policies | By 2006 the National Poverty Reduction Strategy was conceptualized. In the current cycle the NPRS was widely discussed and incorporated into the Belarus Socio-economic Development Programme for 2006 – 2010 and in the State Employment Programme for 2006-2010 |
| UNDP Contribution: CP Outputs: (a) Broad and constructive policy dialogue facilitated to discuss the National Poverty Reduction Strategy (NPRS) and poverty-related programmes and action plans; Progress and Achievements: Representatives of the government, business community, church and civil society formed a broad platform to discuss the basic Foundation of the National Poverty Reduction Strategy in Belarus. The final version of the NPRSP incorporated findings from extensive background research, feedback from policy practitioners, the civil society and international peer reviewers. Portions of the document have been incorporated in the Belarus Socio-economic Development Programme for 2006 – 2010 and in the State Employment Programme for 2006-2010. An awareness and recognition of the poverty-related issues by policy makers and the general public was increased and contributed to generating the political will to develop and implement poverty reduction measures. It has reinforced the perception that successful socio-economic development will be impossible unless poverty is kept under control. UNDP continues to assist the government in improving the availability and quality of data for social diagnostics and early warning of high unemployment and poverty risks at the regional level. |
| 3. Enhanced state and local capacity for socio-economic monitoring and formulating policies aimed at avoiding rising poverty levels, unemployment and social tensions in small communities as a result of industrial and agricultural reforms and enterprise restructuring | 10 | Number of mono-industry towns in a group of risk of high unemployment and poverty | A Comprehensive Poverty analysis ( 2005) revealed that Poverty incidence was much higher in rural areas and especially in small mono-company towns (44 small towns). Adoption and implementation of the State Programme of small towns development for 2007-2010 led to decreasing of poverty levels, unemployment and social tensions in small communities. |
| UNDP Contribution: CP Outputs: Early-warning system introduced to prevent mono-industry towns from negative effects of core enterprise restructuring. Progress and Achievements: A wide advocacy campaign was undertaken by UNDP to demonstrate that sustainable development in single-enterprise towns demands new state policies that would promote restructuring and industrial revival, while facilitating social dialogue and pursuing a range of interventions to reduce the risk of unemployment, social exclusion and poverty. Thus, UNDP contributed to initiating development of the relevant government policy and particular state programme addressing problems of mono-industry towns in Belarus. |
| 4. Business climate for investors and domestic private sector improved through developing public-private partnerships | 1,024 | Growth of the number of SMEs, share of SMEs in the GDP, number of employees | a. In 2006 the share of GDP produced by SMEs was 8,2% and 9,3%, in 2008; the number of SMEs increased from 2.8 small business per 1000 population (2006) to 7,03; the number of employees increased by 1,4 times (from 456,180 (2005) to 643,832 (2008)); |
| UNDP Contribution: CP Outputs: (a) Multi-stakeholder dialogue and mechanism in place to foster partnership of business associations and government agencies to lobby the interest of private sector while drafting legal regulations; Progress and Achievements: UNDP strengthened dialogue and partnership between business and the state by making it more constructive and specific. It elevated the role of businesses as partners in developing current and future policies affecting the private sector. It also helped make the policy making processes more transparent, and decrease the state involvement in the economy. Several policy notes were produced such as reduction of tax burden, simplification of SMEs rent conditions which were subsequently enacted through relevant Decrees of the President and the Government. Policy recommendations are also reckoned in the State Plan on Liberalization of Economy for 2009. |
| 5. Increased alternative economic opportunities for sustainable development of small towns and rural areas | 217 | New facilities set up to serve vulnerable groups to improve their employability and assist in starting business | Explicit need and demand revealed in 2006 from the business community was to avoid youth unemployment and promote entrepreneurial culture; by the end of the programme, the capacity of SME support institutions was enhanced to serve vulnerable groups to improve their employability and income-generating (youth, women and rural population); a number of Small Business Development Centers increased from 38 (2007) to 52 (2009). |
| UNDP Contribution: CP Outputs: SME support institutions developed and vulnerable groups supported in improving employability and income generating Progress and Achievements: the legal environment for small business support institutions was improved; capacity of the SME infrastructure was enhanced by promoting adoption of marketing technologies and approaches to serving SMEs, establishing a bank of guidebooks on operating businesses in various sectors with client bases in rural areas and small cities. Three small business development centers became better equipped and focused on improving access to markets, information, assets, and opportunities for the population living in small towns and remote/rural areas. Particular emphasis was placed on the development of inclusive financial services, promotion of microfinance and enhancement of financial culture of the low-income population. Through the global compact initiative UNDP promoted responsible entrepreneurship and engaged businesses in local socio-economic development: 62 companies and organizations joint the Global Compact; 4 partnership projects with private sector involvement were piloted in such areas as telemedicine, school diet, loan guarantee funds for SMEs, sustainable development of small towns and communities. |
| 6. Multi-stakeholder participation (including women’s networks and experts) to set gender-sensitive development agenda and MDG targets established through economic empowerment of women | 100 | Participation of women in training and public decision-making process Number of women entrepreneurs | Youth multi-service center is being established in Minsk to serve as a model for all the regions on youth employment including young women. The center will also provide training for young men and women on business issues including entrepreneurship and how to set up a business. Facility created for women in Brest and Minsk region to set up private enterprises |
| UNDP Contribution: CP Outputs: Facilitated partnerships of women’s NGOs and public agencies supported to address issues on gender equality and employment promotion Strategic partnership supported to combat trafficking in women and assist in rehabilitation of victims of trafficking. Project on women’s entrepreneurship initiated Progress and Achievements: UNDP established strong partnerships with local and regional authorities, local NGOs, UNICEF and donors and enhanced conditions for women’s entrepreneurship in Brest and Minsk regions through provision of trainings and information campaigns. A shelter for women victims of trafficking is supported together with LaStrada programme. UNDP and the Ministry of Interior hold regular partnership meetings to discuss burinign issues and cooperation in the area of THB. UNDP also assisted the government in creation of better conditions for rehabilitation of victims including social and legal support, trainings on entrepreneurial skills. |
| 7. Increased citizens’ participation in policy dialogue and increased local development through enhanced access to ICT and development of ICT tools | 3 | ICT access and availability for NGOs and general population | Facility was created for Internet access in libraries, schools, universities, parliament and state institutions. Local population has access to internet cafes and the post offices all over the country provide access to Internet and e-mail services for everyone. |
| UNDP Contribution: CP Outputs: Increased regional access to Internet and capacity-building through projects on ICT for development. Project on legal training and legal assistance (e.g. Legal Clinics) Progress and Achievements: As a result of interventions in ICT area that UNDP had in 1996-2004 the Government took leadership in implementing state programmes that promoted ICT access to population without requesting UNDP’s support after the completion of Internet II project in 2004. As a result of UNDP’s project on legal clinics the Ministry of Education issued an internal instruction in which all the universities in the country where there is a legal faculty are obliged to set up legal clinics and provide free of charge assistance to the vulnerable groups. While initiating a new project in this area UNDP received a letter from the Ministry of Education with official deny for cooperation in this area due to the fact that there is an internal instruction on legal clinics and there is no need for any new interventions in this area. |
| 8. Mechanisms for national Local Agenda 21, integrating of economic, social and environmental issues, adopted and implemented | 240 | Number of regional/local municipalities involved in sustainable development activities | 35 local municipalities are involved in sustainable development activities |
| UNDP Contribution: CP Outputs: Local Agendas 21 are prepared; Projects on development of methodological and legal basis for sustainable development (e.g. on Strategic Environmental Assessment) and Local Agendas 21; Projects on support to NGOs (ICT, communication, capacity-building, training, etc.) including GEF Small Grants Programme Progress and Achievements: 1.1. Intensive information campaign aiming at raising population awareness of sustainable development and Local Agenda 21 (LA21) conducted in all the 6 Belarusian regions; 1.2. 35 pilot communities have been selected for development of LA 21 (to be developed in 2010). 2. National institutional and expert capacity for Strategic Environmental Assessment (SEA) is being developed through an on-going project on SEA financed by the European Union and UNDP. |
| 9. Clean energy technologies promoted through energy efficiency, application of renewable energy sources, and technology demonstration/leapfrogging, to reduce emissions | 3,600 | Annual CO2 emissions reduced | The annual greenhouse gas emission (CO2 equivalent) has been reduced by 22,505 tons |
| UNDP Contribution: CP Outputs: 1. Local financing for energy efficiency increased 2. National Energy-efficient Housing Programme Progress and Achievements: 1. Local financing allocated for energy efficiency improvements increased by US$ 10.99 mln. 2. “Integrated Programme for Designing, Construction and Retrofitting of Energy-efficient Residential Buildings for 2099-2010, and up to 2015” approved in June 2009. |
| 10. Multi-stakeholder mechanisms in place to identify opportunities prepare proposals and implement sustainable land management projects | 1,100 | Eroded and erosion prone area | 22,396.7 ha of eroded territory restored. |
| UNDP Contribution: CP Outputs: Mechanism for implementation of National Action Programme (NAP) under the UN Convention to Combat Desertification Progress and Achievements: The National Programme for Combating Land Degradation, including an Action Plan, has been drafted, discussed with the main stakeholders, including the general public, and approved by the Belarusian Ministry of Environment. The Programme is expected to become operational in 2010. A regulatory document, Code of Common Practice, regulating restoration of degraded peatlands in Belarus is in force since January 2009. |
| 11. Biodiversity, ecosystem services, protected areas and other commitments under the Convention on Biological Diversity and other multilateral environmental agreements integrated into national governance and production systems (including social, economic and policy frameworks such as MDGs, NSSEDS and key sectors such as agriculture, forestry, energy, and flood control) | 6,009 | Protected areas, ha | By 2006, the area of specially protected natural territories was 7.6% of the country’s territory. Currently, the specially protected natural territories occupy 8.3% of the country’s territory. |
| UNDP Contribution: CP Outputs: Programme for protection of Polesie biodiversity operational Progress and Achievements: The “National Programme for the Development and Management of the Protected Area System until 2015” is operational since December 2007. The National Strategy and Action Plan for Conservation and Sustainable Use of the Belarus’ Biodiversity” drafted, discussed with the main stakeholders, including the general public, and approved by the Ministry of Environment. The Strategy is expected to become operational in 2010. |
| 12. Create favourable conditions for socio-economic development of the Chernobyl-affected areas | 5,922 | Increase in economic activities (number of new initiatives covered by the programme in the districts, amount of investments into economically active spheres, increase in employment rate, increase in production of clean products and increase in the competitive advantage of these products, market expansion) Increase in citizen active participation | 174 project initiatives were developed and discussed with local and regional stakeholders, donors and government institutions; 500 of private households received new technologies of growing clean products (cucumbers, tomatoes, potatoes, onions, etc.) and had access to micro credits to purchase seeds and livestock. Citizens of four Chernobyl-affected districts (Stolin, Slavgorod, Checherk and Bragin) developed project initiatives together with local government partners and donors and were actively involved in the implementation of those that received donor funding |
| UNDP Contribution: CP Outputs: Affected districts actively involved in sustainable development activities through CORE programme and other initiatives in affected territories. Progress and Achievements: In addition to support the government in CORE programme implementation, UNDP had a number of other interventions that assisted in achieving outcome targets. Promotion of wider and sustainable application of radiation safety measures by local communities and households was very effective in the “Family Health” project that contributed to establishment of a system aimed at building capacity of rural medical and educational professionals to act as consultants on healthy lifestyles and practical radiation safety skills, as well as advocates and catalysts of responsible behavior. The Information and Advisory Centre “Dialogue” created within the project serves as a resource point for this matter. UNDP supported outputs also contributed to increase in citizen active participation through the Health Fairs organized in 8 settlements of the Stolin District and by involving local communities and residents of the four Chernobyl-affected districts of Belarus covered by the CORE Programme in the process of reviewing and refreshing project proposals that had still been in search for donor funding. An experience exchange round table is organised for 50 medical and educational professionals. Funding was secured from the UN Trust Fund for Human Security for the project “Enhancing Human Security in the Chernobyl Affected Areas of Belarus” one of the main focuses of which is on increase in the socio-economic activities of the four affected districts. |
| 13. Institution/legal/policy frameworks established to promote and enforce accountability, transparency and integrity in public service; and conditions for combating of trafficking in human beings and drugs are created | 22,492 | Creation of conditions for effective combating of trafficking in human beings and drugs Creation of conditions for effective combating illegal migration Wider application of human rights in the justice system and in the public administration. | Conditions for effective combating of trafficking in human beings and drugs have been created through changes in the national legislation that were introduced in 2006-2008 into the national legislation Centre for illegal migrants is established in Brest and justice professionals provided with human rights standards training. The first National Survey on drug use is conducted and results publicised. A concept of the law on Administrative Procedures Reform is elaborated in line with the best international practices in this field and according to relevant Human Rights standards. Justice system professionals have been exposed to international human rights standards, provided with sufficient access to relevant literature and discussed improvement to the national legislation |
| UNDP Contribution: CP Outputs: Projects on improvements in the process of development of legal acts (e.g. Impact Assessment) and on enhancement of the state agencies’ ability to promote transparency and accountability including drug trafficking prevention, Belarus-Ukraine-Moldova Anti-Drugs programme (BUMAD), and border management. Progress and Achievements: Advisory support was given by the Government Working Group towards a Concept Paper on the creation of a juvenile justice system in Belarus. Access to international human rights standards and exposure to the international good practices enhanced considerably through study visits (3) and final conferences (on 7 themes), finalization of experts’ reports and recommendations on 12 project themes; printing and dissemination among legal professionals of four-volume compilation (on paper, 8,000 copies and on CD, 10,000) of the international human rights standards and case law; availability of the compilation through Internet UNDP assisted the government in elaboration of a draft law on administrative procedures for a HR-based APR in line with best international practices. The law was ratified. Study tours abroad exposed Belarusian civil servants to international best practices on APR. The project contributed to raising citizens’ awareness of their legal rights and how to claim them. UNDP continued providing support to the government and NGOs in combating illicit drugs. Assistance was provided to the K-9 centre of the Interior Ministry and to National Forensic Laboratory through training, supply of equipment. Belarus Centre for Drugs Monitoring produced Annual Drugs Reports. Regional cooperation of law enforcement agencies improved through several regional events on controlled deliveries of drugs, search of clandestine laboratories and on adjudication of drug-related offences for judges and prosecutors organized jointly with UNODC. |
| 14. Development and implementation of comprehensive Programme to support national efforts to respond to HIV/AIDS | 22,300 | New programme of prevention developed and implemented. Increase in number of infected people treated. | In 2004 the Global Fund to fight AIDS, TB and Malaria allocated its first grant on HIV/AIDS to Belarus. As a result of the grant comprehensive interventions targeting most at risk populations have been launched. In 2004 only 6 people were receiving ARV treatment provided by the government. At the end of 2009 more than 1,800 adults and children are receiving this life saving treatment paid by the grant of the Global Fund. |
| UNDP Contribution: CP Outputs: National programme to prevent/treat HIV/AIDS supplemented by the resources of the Global Fund to Fight HIV/AIDS, TB and Malaria 1. number and percentage of patients receiving ARV treatment 2. number and percentage of vulnerable groups (Intravenous drug users -IDUs, commercial sex workers -CSW, men having sex with men - MSM, prisoners, youth) covered with HIV prevention activities 3. Number and percentage of institutions using centralized information and analytical system of HIV/AIDS data collection Progress and Achievements: Since the beginning of the Round 3 HIV grant to Belarus large scale interventions took place. For instance, since 2004 1836 people including children and prisoners have been receiving ARV treatment, 28,500 IDUs, 16,355MSM, 7,345 FSW and 69,425 prisoners have been reached with HIV prevention activities. 24 institutions have been connected to centralized database on HIV data collection. |
| 15. Unified standards for country-level monitoring and evaluation system created | 9,539 | Unified standards for country-level monitoring and evaluation system created | Before 2007 the country used its own TB reporting system which did not comply with WHO requirements. In 2007, paper based reporting system based on WHO requirements was introduced. In 2009, thanks to the Global Fund’s grant electronic database has been developed. |
| UNDP Contribution: CP Outputs: 1) Number of new smear-positive TB cases detected 2) Number and percentage of TB patients counseled and tested for HIV 3) Number of healthcare providers trained in DOTS 4) Number and percentage of TB dispensaries using the new national TB register and conducting TB surveillance in accordance with WHO recommended standards 5) Number and percentage of laboratories with proper equipment, trained staff and quality control to conduct quality TB diagnosis 6) Number of TB patients reached with social support during directly observed treatment (DOT) 7) Number of TB patients receiving treatment with first-line TB drugs Progress and Achievements: Thanks to the TB grant provided to Belarus by the Global Fund to Fight AIDS, TB and Malaria, significant progress has been achieved in the first two years of the grant’s implementation. TB detection rate improved from 1,235 in 2005 to 1,446 smear positive case detected in 2009, Belarus reached almost 99% of TB patients with HIV testing, as many as 4,153 health care providers have been trained, all TB dispensaries began using internationally accepted reporting forms, 41 laboratories have been equipped which improved TB diagnostics, 2,773 patients have been reached with outpatient treatment programme with social support, 3,674 patients and 200 patients have been receiving treatment of first and second line TB drugs. |
| II. Summary of evaluation findings (e.g. from outcome and project evaluations, UNDAF reviews, and other assessments) In 2009 Mid-term review of the current CPD was conducted by independent evaluators. In general terms the evaluation was positive. The evaluation highlighted that in recent years UNDP has been by far the largest technical assistance and development agency in Belarus. UNDP’s inclusive and apolitical approach has allowed donor-funded projects to emerge in Belarus that would not have done so without it. This would have been to the detriment of the country. It has also helped the government develop its policies in a range of key areas. While UNDP’s partial monopoly on development work may be about to end, its continued good relations with the government should have positioned it well for the future. In general the projects have fulfilled most of the CPD targets. Where they have not done so it is often because either government policy has changed or the targets were poorly conceived in the first place. |

III. Country Programme Resources

| Focus Area | Programme Expenditure ($) | % of Total |
| --- | --- | --- |
|  | Regular (TRAC) | Other | Total |  |
| Poverty and MDGs | 1 450 | 1 123 | 2 573 | 3.49 |
| Democratic Governance | 1 610 | 20 985 | 22 595 | 30.58 |
| Crisis Prevention and Recovery | 659 | 5 263 | 5 922 | 8.01 |
| Environment and Sustainable Development | 520 | 10 429 | 10 949 | 14.82 |
| Responding to HIV/AIDS | 200 | 31 639 | 31 839 | 43.10 |
| Total | 4 439 | 69 439 | 73 878 | 100 |

Data sources: (please indicate the main sources from which data were obtained for this report.)

Financial reports from the Atlas system; National HIV sentinel surveys held annually, data collected within the M&E systems created by two grants on HIV and TB. National Statistics available for the moment of the preparation of this summary