# Evaluation Plan

# Evaluation Plan for: UNDP Botswana

# Programming Cycle: 2010-2014

Date: 17 December 2008

| Evaluation Title | Partners ( joint evaluations) | Strategic Plan key result area | CPD or CPAP Outcome | Evaluation Completion Date | Key Evaluation stakeholders | Resources for Evaluation & Sources of Funding | Mandatory Evaluation? ( Y/N) | Evaluation Status* | Reports uploaded in ERC? ( Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDAF Evaluation |
| Joint mid-term UNDAF evaluation | UN System | Achieving the MDGs and UNDAF outcomes | CPD in the framework of UNDAF | Q3 - Q4 2012 | GoB CSO UNS | UNS GoB | Y | Pending | N |
| Outcome Evaluation |
| GoB-UN Programme of Cooperation mid-term review | UNS UNDP | Achieving the MDGs and UNDAF outcomes | CPD outcome1 | Q3-Q4 2012 | GoB (key implementing ministries and departments) CSO UNS | GoB Country Programme budget | Y | Pending | N |
| Assessment of Development Results | UNDP | Improved UNS coordination, efficiency and effectiveness | CPD outcome1 | Q2 2013 | GoB CSO UNS | GoB Country Programme budget | N | Pending | N |
| Project Evaluation |
| Mid-term and Terminal Evaluations: Accruing Multiple Global Benefits through integrated Water Resources Management/Water Use Efficiency Planning – A demonstration project for Sub-Saharan Africa | MMEWR | Promoting adaptation to climate change Expanding access to environmental and energy services for the poor | CPD outcome 3 | Q4 2010 (December) Q2 2012 (June) | MMEWR MOA MLH WUC District Council CSOs Private Sector | GEF | Y | Pending | N |
| Terminal Evaluation: Renewable Energy-Based Rural Electrification Project | MMEWR BPC | Expanding access to environmental and energy services for the poor | CPD outcome 3 | Q2 2011 (June) | MMEWR, BPC, District Councils, Local Communities CSOs, Private Sector | GEF | Y | Pending | N |
| Mid-term and Terminal Evaluations: Strategic Partnerships to Improve the Financial and Operational Sustainability of Protected Areas | MEWT Birdlife Botswana | Expanding access to environmental and energy services for the poor | CPD outcome 3 | Q2 2011 (June) Q2 2013 (June) | MEWT CSOs Private Sector | GEF | Y | Pending | N |
| Terminal Evaluation: Incorporating Non-Motorized Transport in the City of Gaborone | MLG GCC | Mainstreaming environment and energy | CPD Outcome 3 | Q4 2010 (December) | MLG, MRT, GCC, MEWT | GEF | Y | Pending | N |
| Terminal Evaluation: Building Local Capacity for Biodiversity Conservation on Okavango Delta | MEWT UB | Promoting adaptation to climate change | CPD outcome 3 | Q2 2011 (June) | MEWT, MMEWR, District Council, CSOs, Local Communities, Private Sector | GEF | Y | Pending | N |
| Other Evaluation |
| Assessment of new interventions (trade, climate change, gender) | UNDP | Improved UNS coordination, efficiency and effectiveness | CPD outcome 1, 2 and 3 | Q2 2013 | UNS, MEWT, MMEWR, District Council, CSOs, Local Communities, Private Sector, WAD, DIT, NACA | GoB Country Programme budget | N | Pending | N |
| Assessment of sub national and community level interventions | UNDP | Key results areas for CPD Outcomes 2 and 32 | CPD outcome 2 and 3 | Q1 2012 | UNS, MEWT, MMEWR, District Council, CSOs, Local Communities, Private Sector, WAD, DIT, MLG, MFDP, NACA | GoB Country Programme budget | N | Pending | N |

* Evaluation Status: Pending, Initiated, or Done

1. National capacities for reaching the NDP 10 objectives, the MDG and Vision 2016 goals built through programmes on public service delivery, human rights, economic diversification, gender equity, HIV and Aids prevention, natural resource management and climate change.

2. CPD Outcome 2:  Promoting inclusive growth, gender equality and achievement of the MDGs & Mitigating the impact of HIV and AIDS; CPD Outcome 3: Promoting adaptation to climate change & Expanding access to environmental and energy services for the poor