Evaluation Plan

Evaluation Plan for: UNDP Timor-Leste

Programming Cycle: 2009-2013

| Evaluation Title | Partners (joint evaluation) | SP Goal | CPD or CPAP Outcome | Evaluation Completion Date | Key evaluation stakeholders | Resources for Evaluation and Sources of Funding | Mandatory Evaluation? (Y/N) | Evaluation Status* | Reports uploaded in ERC? (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDAF Evaluations |
| Joint Mid-term Review of UNDAF | UNDAF agencies | n/a | n/a | 2011 | The TLS Government, UN system, and others including concerned donors and CSOs if applicable | Joint funding by partners | N | Pending | N |
| Mid-term Review of Capacity Development Impact | UNDAF agencies | n/a | n/a | 2012 | The TLS Government, UN system, and others including concerned donors and CSOs if applicable | Joint funding by partners | N | Pending | N |
| Outcome Evaluations |
| Evaluation on UNDP support to Justice sector | n/a | SP Goal 2: To strengthen national and local capacities for democratic governance, building upon the principles of the Millennium Declaration and the World Summit Outcome | Outcome 1: State institutions strengthened through interventions aimed at improving institutional capacity in planning, efficiency, accountability and transparency. | Nov. 2010 | MoJ, Public Prosecutor’s Office, Courts, CSOs | 1 international and 1 national consultant, one month mission. Fund from projects contributing to the outcome. | Y | Pending | N |
| Joint Programme Evaluation (HSTF/ MDGF) | UN agencies participating in the Joint Programme | SP Goal 1: To strengthen national and local capacities to achieve inclusive growth, reduce poverty and inequality and halt the spread of HIV/AIDS | Outcome 3: Vulnerable groups have improved access to livelihoods | June 2011 | MAF, MoED, MoF, Self Help Groups (SHGs), NGOs | 2 international and 1 national consultants, 1.5 month mission. Fund from projects contributing to the outcome | Y | Pending | N |
| Evaluation on Support to the Government Capacity Development of Environmental Resource Management | n/a | SP Goal 4: To strengthen national capacities to achieve sustainable development through environmental management, adaptation to climate change, and expansion of access to environmental and energy services for the poor | Outcome 6: Improved capacities of government institutions and communities for environmental resource management, and implementation of adaptation strategies | June 2012 | SoS of Environment, MoE, Commission D of the Parliament, Inter-Ministry Working Group (IMWG) Environment and Natural Resource Management | 2 international and 1 national consultants, 1.5 month mission. Fund from projects contributing to the outcome | Y | Pending | N |
| Evaluation on UNDP Support to Capacity Development on DRM | n/a | SP Goal 3: To advance human development by strengthening national and local capacities to prevent, mitigate and recover from the effects of violent conflicts and natural disasters. | Outcome 7:National capacity for restoring the foundations for development following conflict or disaster developed | June 2013 |  | 2 international and 1 national consultants, 1.5 month mission. Fund from projects contributing to the outcome | Y | Pending | N |
| Project Evaluations |
| Nil |  |  |  |  |  |  |  |  |  |
| Other Evaluations |
| Nil |  |  |  |  |  |  |  |  |  |

* Evaluation Status: Pending, Initiated, or Done