###### Status Table - Simplification and Harmonization of Rules and Procedures January 2004

| Deliverables | Milestones | Responsibility | Status in January 2004 |
| --- | --- | --- | --- |
| PROGRAMME IMPLEMENTATION MODALITIES |  |  |  |
| Programme Preparation and Approval 1. UNDAF results matrix | Revised procedure incorporated in the CCA and UNDAF Guidelines issued in October 2003 | UNDG ExCom Agencies | ( Completed 2003. 6 countries completed Matrix in 2003, 19 Counties in 2003/early 2004, 19 in 2004/2005. |
| 2. Joint Strategy Meetings for CP Formulation | Procedure incorporated in the CCA and UNDAF Guidelines issued in October 2003 | UNDG ExCom Agencies | ( Completed 2003. Guidelines completed in 2003. [Introduced in 6 countries in 2003, 19 Countries in 2004, 19 in 2005.] |
| 3. Harmonized terminology and structure for the programme and project documentation | Common name and structure for document going to the Executive Boards developed, starting with the five countries that are submitting Country Programmes to the 2003 Boards | UNDG ExCom Agencies | ( All Completed in 2002 and 2003, introduced starting with the six countries in 2003 |
| 4. Harmonized Results Based Management terminology | Procedure incorporated in the CCA and UNDAF Guidelines issued in October 2003 | UNDG ExCom Agencies | ( Completed in 2003 (roll out starting with the six countries in 2003) |
| Programme Implementation 1. Country Programme Action Plan (CPAP) | New procedure approved at the 17 January 2003 Joint PG/MG. Harmonized format for 5-yaer plans of operation for each ExCom agency | UNDG ExCom agencies | ( Completed in 2003 (roll out starting with the six countries in 2003) |
| 2. Annual Work Plan (AWP) | New procedure approved at the 17 January 2003 Joint PG/MG. Harmonized procedures to plan and monitor progress towards outputs with implementing partners. | UNDG ExCom agencies | ( Completed in 2003 (roll out starting with the six countries in 2003) |
| 3. Revised Guidance Note on Joint Programming | Agencies’ desk review Country Visits Interdisciplinary approach (different working groups involved) Fund management options identified & described Joint Programming VS Joint Programme | UNDG ExCom Agencies | Completed in 2003 for 2004 roll out |
| 4. Operational Guidelines for National Execution | Best Practices in Efficiency, Effectiveness of Programme Implementation, Capacity Building and Accountability Reviewed, 2002-2003 In line with CCPOQ guidelines, more specific, operational guidelines developed to be used by all ExCom Agencies and applicable to all countries with the view to improving efficiency and effectiveness, maximizing national capacity building, and improving accountability, 2004 | UNDG ExCom Agencies | In progress The framework for resource transfer modalities is currently being finalized and will be introduced starting January 2005. |
| Programme Monitoring, Evaluation and Reporting 1. Recommendations for Standardization and Simplification of Project Reporting | Format and practices for standardized reporting, including to donors, annual project reports and other recommendations related to simplification reporting developed, 2003 | UNDG ExCom Agencies (in collaboration with donor community) | ( Completed in 2003 Standard Progress Report Completed in 2003 and being introduced. |
| 2. Access to Evaluative Information | Interagency access to agencies’ monitoring and evaluation web sites operationalized to ensure horizontal learning | UNDG ExCom Agencies | ( Completed and operational starting 2003 |
| 3. UNDAF M&E plan and UNDAF Evaluation | Procedure incorporated in the revised CCA and UNDAF Guidelines issued in October 2003 | UNDG ExCom Agencies | ( Completed in 2003, being introduced starting with the six countries in 2003 |