# Evaluation Plan Template

# Evaluation Plan for: Jordan

# Programming Cycle: 2008-2012

Date: February 2007

| Evaluation Title | Partners (joint evaluation) | MYFF Goal | CPD or CPAP Outcome | Evaluation Completion Date | Key evaluation stakeholders | Resources for Evaluation and Sources of Funding | Mandatory Evaluation? (Y/N) | Evaluation Status* | Reports uploaded in ERC? (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDAF Evaluations |
| UNDAF Mid Term Review | UN Agencies | 1, 2, 3 and 4 | All | 3rd Quarter 2010 | UN Agencies Government, UNDAF counterparts | UN Agencies & UN Resident Coordinator Office | Y |  |  |
| Outcome Evaluations |
| Outcome 2.2 Evaluation |  | 2: Democratic Governance | 2.2.1 Uniform and transparent systems for accounting, procurement and property tax collection systems set up and operational. 2.2.2 National decentralization “Regionalization Framework” reformulated and related implementation action plans prepared 2.2.3 Capacity of the Ministry of Public Sector Development enhanced to improve service delivery at pilot line ministries 2.2.4. Institutional capacity of Anti-Corruption Commission built up | 4th Quarter 2009 | Ministries of Planning, Finance, Municipal Affairs, and Public Sector Reform. Selected Municipalities in Jordan. Anti-Corruption Commission. Private sector entities. Local CSOs. | Programme Resources will be allocated under each initiative. | Y |  |  |
| Outcome 1.1 Evaluation | Joint Evaluation with UNIDO | 1: Achieving MDGs and reducing human poverty | 1.1.2 Increased employment skills and work opportunities for women, young people, food in-secure farmers, and persons with disabilities in under-served areas. | 1st Quarter 2010 | Ministry of Industry and Trade. Ministry of Planning. Local NGOs. Local communities Private sector entities. | Programme Resources will be allocated under each initiative. | Y |  |  |
| Outcome 3.2 Evaluation | Joint evaluation with GEF | 3: Energy and Environment for Sustainable Development | 3.2.1 Policy relevant capacities for the implementation of the global environment conventions are developed 3.2.2 Climate change adaptation streamlined in national action plans in ways that protect the vulnerable groups 3.2.3 The protection and sustainable use of agricultural resources and biological diversity included in relevant national and sectoral plans particularly for major hotspots 3.2.4 Policy options for higher energy efficiency | 2nd Quarter 2011 | Ministries of Environment, Energy, Health and Transport. National Energy Research Centre. Royal Society for the Conservation of nature. BirdLife International | Programme Resources will be allocated under each initiative. | Y |  |  |
| Outcome 3.3 Evaluation | Joint evaluation with GEF | 3. Energy and Environment for Sustainable Development | 3.3.1. Enhanced national capacity to implement the National Implementation Plan related to persistent organic pollutants (POPs) in accordance with the Stockholm Convention. | 4th Quarter 2011 | Ministries of Environment, Health and Agriculture | Resources will be allocated under the initiative. | N |  |  |
| Project Evaluations |
| Building the Capacity of the Ministry of Planning and line ministries in monitoring and evaluation of the MDGs action plans | UN Agencies (UNFPA and UNIFEM) | 2: Democratic Governance | 2.1.4 Strengthened capacities for monitoring progress towards the National Agenda and the MDGs aligned with CRC, CEDAW and other human rights obligations | 4th Quarter 2011 | Ministry of Planning/ Monitoring and Evaluation Department. M&E sections at line ministries. | Resources will be allocated under the initiative. | N |  |  |
| Other Evaluations |
| CPD Mid Term Review |  | 1,2,3 and 4 | All | 2nd Quarter 2010 | Ministry of Planning. | Programme Resources will be allocated | N |  |  |

* Evaluation Status: Pending, Initiated, or Done

2/2

# Text boxes

1/2