Evaluation Plan

Evaluation Plan for: CPD Indonesia

Programming Cycle: 2011-2015

Date: 21 April 2010

| Evaluation Title | Partners (joint evaluation) | Strategic Plan Results Area | CPD / CPAP Outcome | Evaluation Completion Date | Key evaluation stakeholders | Resources for Evaluation and Sources of Funding | Mandatory Evaluation? (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome Evaluations |
| 1. Midterm-Evaluation of the CPD |  | All CPD results areas | &1.2; 2.1 & 2.2; 3.1&3.2; 4.1 | Second half of 2013 | Bappenas & UNDP | Cross selection of major programmes |  |
| 2. Outcome Evaluation: Environment and Energy | FAO, UNEP, ICRAF, Ford Foundation, UNOPS | Environment and Energy | 2.1 and 2.2 | Nov 2013 | Bappenas, Min of Environment, UNDP | SCBFWM Project (GEF LD & Biodiversity); and ATSEA Project (GEF IW) | Yes |
| 3. Outcome Evaluation: Democratic Governance |  | Democratic Governance | 3.1 and 3.2 | October 2014 (after the Election) | Bappenas, Min of Home Affair, UNDP | AGTP & NITP Project | Yes |
| 4. Outcome Evaluation: Crisis Prevention and recovery |  | Crisis Prevention and recovery | 4.1 | August 2014 | Bappenas, UNDP | PTD project SC-DRR | Yes |
| 5. Outcome Evaluation: MDGs and Poverty Reduction |  | MDGs and Poverty Reduction | and 1.2 | September 2014 | Bappenas and UNDP | PDP and TBD | Yes |
| Project Evaluations |
| 1. PTD | Netherland | Crisis Prevention and Recovery | 4.1 | June 2012 | Bappenas | PTD | No |
| 2. SC-DRR | DFID, AusAid | Crisis Prevention and Recovery | 4.1 | December 2012 | BNPB, MOHA | SC-DRR | No |
| 3. PDP |  | MDGs and Poverty Reduction | 1.2 | June 2011 | Bappenas, Bappeda Papua and West Papua | PDP | No |
| 4. AGTP | MDF | Democratic Governance | 3.1 | June 2012 | Bappenas, Depdagri, Pemda Aceh | AGTP | Yes |
| 5. NITP | MDF | Democratic Governance | 3.1 | June 2012 | Bappenas, Depdagri, Pemda Nias | NITP | Yes |
| 6. MCTAP |  | Environment & Energy | 2.1 | June 2013 : final Evaluation | Agency for Assessment and Application Technology | GEF Funding | Yes |
| 7. BRESEL |  | Environment & Energy | 2.1 | June 2014: Final Evaluation | DG of Electricity and Energy Utilization | GEF Funding | Yes |
| 8. SCBFWM |  | Environment & Energy | 2.2 | December 2013 | Min of Forestry and Bappenas | GEF Funding | Yes |
| 9. ATSEA | UNOPS | Environment & Energy | 2.2 | December 2013 | Agency for Marine and Fisheries and Bappenas | GEF Funding | Yes |
| Other Evaluations |
| UNDAF Midterm Evaluation | All resident UN Organization | All four above | Aggregation of all | June 2013 | Government and UN Organizations | All resident UN Organization | N |