Evaluation Plan (draft as of 18 December 2008)

Evaluation Plan for: UNDP TAJIKISTAN CPD

Programming Cycle: 2010-2014

Date: December 2008

| Evaluation Title | Partners (joint evaluation) | Strategic Plan Focus area | CPD or CPAP Outcome | Evaluation Completion Date | Key evaluation stakeholders | Resources for Evaluation and Sources of Funding | Mandatory Evaluation? (Y/N) | Evaluation Status* | Reports uploaded in ERC? (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDAF Evaluations |
| Joint mid-term UNDAF evaluation (overall and select themes) | UN system | Poverty reduction and support to the MDGs | CPD in the framework of UNDAF | Q3 - Q4 2012 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| Outcome Evaluations |
| Poverty reduction and economic development programmes are enhanced, with particular focus on the rural poor, women and marginalized people. | Ministry of Economic Development and Trade, Ministry of Finance, State Committee on Coordination of Foreign Aid and Investments and State Property, Regional MFIs, National Bank of Tajikistan. | Poverty reduction and support to the MDGs | CPD | Q3 – Q4 2013 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| Halt the spread of HIV/AIDS and TB epidemics and eliminate Malaria by 2015 in line with MDGs. | Ministry of Health, Regional & local health departments, MoJ, MoLSP, State youth committee, CSOs, PLWH, UN agencies, mass media, religious leaders international NGOs | Poverty reduction and support to the MDGs | CPD | Q3 – Q4 2012 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| National and local levels of government have the capacity to implement democratic governance practices, and effectively and strategically plan, finance and implement development initiatives in an inclusive and participatory manner. | Executive Office of the President, MFA, MoED and Trade, MoF, MoJ, Ministry of Security (Border Forces)/ Customs Committee, Majlisi Oli (Parliament), Agency on Anti-corruption and Financial Control; State Statistical Agency. | Democratic governance | CPD | Q3 – Q4 2011 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| Decreased risk of natural and man-made hazards to rural and urban livelihoods; infrastructure and recovery mechanisms in place. | Committee on Emergency Situations, REACT Partners, ECHO, International and national NGOs, District authorities. | Crisis prevention and recovery | CPD | Q3 – Q4 2012 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| Government is able to plan, coordinate and implement comprehensive mine action. | Tajikistan Mine Action Centre, Swiss Foundation for Demining (FSD), OSCE, Ministry of Defence, Red Crescent Society of Tajikistan. | Crisis prevention and recovery | CPD | Q3 – Q4 2014 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| Sustainable natural resources management, improved environmental protection, and increased access to alternative renewable energy. | Committee for Environmental Protection, Ministry for Land Reclamation and Water Resources, State Committee for Land Management, Bio-diversity and Cartography, National Biodiversity and Bio-safety Center, Agency for Hydro-meteorology, Ministry of Agriculture, NGOs. | Environment and Sustainable Development | CPD | Q3 – Q4 2013 | NPC/line ministries/ state departments/district administration/CBOs/private sector | $50,000 Country Programme budget | Y |  |  |
| Other Evaluations |
| Country Programme mid-term review | CO/UN System/ National Stakeholders |  | CPD | Q4 2012 | UN system/ other partners | $50,000 Country Programme budget | N |  |  |

- Evaluation Status: Pending, Initiated, or Done

- This Evaluation Plan is subject to change